## INSTRUCTIONS
THE SECURE CLOUD MIGRATION FRAMEWORK
This template is provided as a self-help tool to help organizations like yours successfully and securely migrate applications to the cloud and realize benefits as early as possible. You may want to incorporate these elements into your Jira or other project management tools for better overall management. Keep in mind that there may be elements unique to your environment that this template doesn't address and that you will want to add. Along those lines, feel free to use and modify the elements in this template as you see fit for your purposes.
For questions or to consult with Armor regarding your secure migration needs, please contact us:
US: +1 877 262 3473
UK: +44 800 500 3167
Last revised - August 2019

## FRAMEWORK STAGES
STAGES
Before you take your first step toward migrating applications to the cloud, you need to step back and consider what your organization’s overall cloud strategy and policies will be (Review the STRATEGIZE tab). As the cloud represents a fundamental departure from traditional on-premise IT and related security and compliance approaches, your organization has an opportunity to capitalize on the speed, efficiencies and cost advantages of the cloud from a security and compliance standpoint as well. In other words, the cloud represents a ‘do over’ as well as a way to significantly elevate your organization’s security and compliance posture.
Use this sheet to track progression of the migration. We recommend using this sheet for a specific application. If you have more than one application, just copy and paste the sheet to additional tabs as needed.
ASSESS & PLAN
STEPS | STATUS | OWNER | DUE DATE
CLOUD STRATEGY FORMULATION
Assess Internal Staff Expertise
- Assess Team Members
- Assess Need for Cloud Migration Partner
DEVELOP THE BUSINESS CASE
Assess the Environment
- Discovery: Applications
- Discovery: Data
- Discovery: Infrastructure
- Discovery: Servers
- Discovery: Tools
- Discovery: Cloud Services (Shadow IT)
- Perform Manual Audit Spot Checks
Articulate Requirements [For application]
- Identify best cloud/other platform(s) for hosting
- Assess performance requirements
- Assess data handling requirements
- Assess scale and importance of applications
- Determine if production or development app
- Assess Operating System requirements
- Identify secondary or accompanying processes
- Assess database, storage and ancillary needs
- Identify geographic support requirements
- Identify requirements for redundancy
- Identify specialized performance requirements
<Sec> Identify current security controls
<Sec> Capture access privilege information
<Sec> Identify applicable compliance frameworks
<Sec> Assess controls around comms/data flows
<Sec> Capture backup practices
Identify Additional Risks
Determine Migration Strategy
Assess Cloud Capabilities
<Sec> Discover Shadow IT
<Sec> Assess native IAM capabilities
<Sec> Inquire on CSP attestations
<Sec> Assess native encryption services
<Sec> Assess native security capabilities
<Sec> Assess data flows into existing workflows
Assess Tool Requirements
- Identify native tools
- Identify third-party tools
- Identify applicable in-house tools
Determine Budget
- Itemize current costs
- Assess cloud migration and hosting costs
Calculate ROI
BUSINESS CASE APPROVAL
Form CCoE
<Sec> Establish access controls for team members
PLANNING
Define a Proof-of-Concept(s)
- Revew CSP partner network for options
- Identify security and compliance control requirements per workload
- Identify Cloud Workload Protection capabilities
Draft Plan/Project Charter Formulation
- Articulate a clear scope including projects and sub-projects as well as sub-tasks.
- Identify responsible parties/Use RACI
- Identify milestones and deadlines
- Identify dependencies and risks
- Detail a communications plan
- Capture budget requirements
- Define KPIs
- Identify required skillsets and necessary hiring
- Assess need for a Project Management resource
PLAN APPROVAL
VALIDATE
STEPS | STATUS | OWNER | DUE DATE
DEVELOP YOUR POC
<Sec> Review and incorporate OWASP secure code development practices, if applicale
<Sec> Review and incorporate the Well Architected Framework
<Sec> Review required security and compliance controls for additional areas to address.
<Sec> Implement Multi-Factor Authentication
<Sec> Employ encryption for data in transit/at rest
<Sec> Implement Cloud Workload Protection
VALIDATE YOUR POC
- Business Requirements
- Customer Requirements
- Operational Requirements
- Performance Requirements
- Security and Compliance Control Requirements
- Security Operational Requirements
- Cost Requirements
DECISION-GATE
BUILD
STEPS | STATUS | OWNER | DUE DATE
PERFORM A PILOT
<Sec> Review and incorporate OWASP secure code development practices, if applicale
<Sec> Review and incorporate the Well Architected Framework
<Sec> Engage Security, IT and/or DevOps teams
<Sec> Review required security and compliance controls for additional areas to address.
<Sec> Implement IAM.
<Sec> Hash and salt databases, as applicable
<Sec> Implement a Patch Management methodology
<Sec> Implement Multi-Factor Authentication
<Sec> Employ encryption for data in transit/at rest
<Sec> If using APIs, perform testing to validate that APIs are secure
<Sec> Implement Cloud Workload Protection
<Sec> Validate security of new tech/tools
<Sec> Ensure monitoring and associated staffing is in place
<Sec> Implement a backup policy and regimen
<Sec> Run a cloud security posture assessment
<Sec> Validate that all controls are operable and sending event telemetry successfully
Outline Testing
- Application Testing Requirements
- Infrastructure Testing Requirements
- Usability and User Acceptance Testing Requirements
- Performance Testing Requirements
- Security and Compliance Testing Requirements
Assess Cost
Establish Monitoring and Reporting
Communicate
Contracting
PUT THE PIECES IN PLACE
Leverage Partner Networks
Automate Deployment
Have a Contingency Plan
Move Groups
DECISION-GATE
MIGRATE
STEPS | STATUS | OWNER | DUE DATE
Perform Backups
Ensure Team Readiness
Communicate
MIGRATE
<Sec> Implement Cloud Security Posture Management
<Sec> Implement a Patch Management methodology
<Sec> Implement Multi-factor Authorization practices
<Sec> Implement IAM
<Sec> Implement encryption
<Sec> Implement segmentation
<Sec> Validate that APIs are secure
<Sec> Implement Cloud Workload Protection
<Sec> Ensure that monitoring and associated staff in in place
<Sec> Conduct penetration testing
<Sec> Enable protection against DoS/DDoS attacks as appropriate
<Sec> Implement DLP as appropriate
<Sec> Conduct Security Awareness Training across employees
Revisit Testing
- Application Testing
- Infrastructure Testing
- Usability and User Acceptance Testing
- Performance Testing
- Security and Compliance Testing
DECISION-GATE
OPTIMIZE
STEPS | STATUS | OWNER | DUE DATE
Measure KPI Performance
Document Everything
Plan for Retirement
Optimize Security Operations
<Sec> Perform analysis of security operations
<Sec> Assess privilege levels and re-review access
<Sec> Analyze logs for unusual access and activity.
<Sec> Analyze alerting and alert triaging
<Sec> Measure False Positive rates and other indicators
<Sec> Analyze vulnerabilities and management processes
<Sec> Tune and optimize security controls
Optimize Response Processes
<Sec> Thoroughly document IR practices for cloud environments
<Sec> Identify and leverage native tools that can aid in forensic investigation
<Sec> Create a process for documenting incidents
<Sec> Track false positives and actions taken to prevent re-occurrence
<Sec> Collect and store logs per policies
<Sec> Identify opportunities for automation including automated remediation
PROJECT SIGN-OFF
- Collect and analyze project indicators
- Calculate projected ROI versus realized ROI to date
- Report on all indicators to stakeholders
DECISION-GATE
POST-PROJECT
- Embrace DevOps
- Leverage Partner Networks
- Stay Current on New Tools
- Accelerate Education
<Sec> Pursue continuous education on cloud security across teams
- Analyze Usage and Cost
Note on B13: See the ASSESS SKILLSETS worksheet.
Note on B26: Check out the APPLICATION ASSESSMENT worksheet.
Note on B185: See PLANNING FOR RETIREMENT worksheet.

## STRATEGIZE
STRATEGIZE
OVERALL PROJECT OWNER | Name/Title
OVERALL PROJECT CHAMPION | Name/Title
ASSESSING DRIVERS
What overall business drivers are pushing your IT/Security/DevOps teams to the cloud? What is behind the business’ and IT’s drive to capitalize on the cloud? Use this to help shape your business plan and the business reasons that may be at play. Rank the top business goals or objectives that are driving investments in cloud computing initiatives in your organization - Rank as many as five that apply from 1 to 5, with 1 being the most important and 5 being the least important.
BUSINESS DRIVER MATRIX | 1 | 2 | 3 | 4 | 5
Improving the speed of IT service delivery
Greater flexibility to react to changing market conditions
Enabling business continuity
Improving customer support of services
Lower total cost of ownership (TCO)
Replacing proprietary technology
Savings on CAPEX (capital expenditures)
Reducing resource waste
Need for real-time information
Faster return on investment
Other (please specify and rank)
What technical drivers are pushing your IT/Security/DevOps teams to the cloud? What does your organization view as the most important technical benefits of cloud computing? Use this to help shape your business plan and why migrating applications to the cloud is so important. Of the factors and drivers below, rank as many as five that apply from 1 to 5, with 1 being the most important and 5 being the least important.
TECHNICAL DRIVER MATRIX | 1 | 2 | 3 | 4 | 5
Cost savings on hardware
Cost savings on software
Cost savings on IT operations staff
Ability to rapidly launch new products and services
Ability to grow and shrink IT capacity on demand
Convenience for the development teams
No upfront investment
Pricing flexibility
Better collaboration across teams
Outsourcing of non-core competencies
Other (please specify and rank)
CLOUD CENTER OF EXCELLENCE (CCoE) TEAM
Area of Representation | Name, Title
Area of Representation | Name, Title
Area of Representation | Name, Title
Area of Representation | Name, Title
Area of Representation | Name, Title
Area of Representation | Name, Title
Area of Representation | Name, Title
APPLICATION STAKEHOLDER MATRIX | NAME/TITLE
Business Champion/Executive Sponsor | Name, Title
Technical Champion/Technical Sponsor | Name, Title
Business Owner | Name, Title
Application Owner | Name, Title
Stakeholder - IT | Name, Title
Stakeholder - Security | Name, Title
Stakeholder - Compliance | Name, Title
Stakeholder - Development | Name, Title
Stakeholder - Engineering | Name, Title
Stakeholder - Legal | Name, Title
Stakeholder - HR | Name, Title
Stakeholder - Customer Operations | Name, Title
FAMILIARITY WITH THE SHARED RESPONSIBILITY MODEL | YES/NO/NOT APPLICABLE
Is your organization versed in shared responsibility as it pertains to Infrastructure-as-a-Service (IaaS)?
Is your organization versed in shared responsibility as it pertains to Platform-as-a-Service (PaaS)?
Is your organization versed in shared responsibility as it pertains to Sofware-as-a-Service (SaaS)?
POLICY | YES (Explain), NO, NOT APPLICABLE
Is your organization concerned for vendor lock-in and/or plan to adopt a Cloud-Agnostic policy for public cloud usage?
- If "Yes," describe the strategy or policy:
Does your organization plan to adopt a multi-cloud strartegy for cloud adoption and usage?
- If "Yes," describe the strategy or policy:
OPPORTUNITY | YES, NO, NOT APPLICABLE
Is your organization versed in container architecture?
Does your organization plan to utilize containers for deployment of applications?
- Preferred container OS(s):
- Preferred container orchestration platform(s):
Is your organization versed in microservices architecture?
Does your organization anticipate utilizing microservices for any applications?

## Assess Skillsets
ASSESS SKILLSETS
Use this worksheet to assess the expertise, skillsets and experience of your team. This can also be applied to selection of your Cloud Center of Excellence (CCoE) team.
TEAM MEMBER
Name:
Cloud Experience (Years):
Cloud Areas of Expertise:
Cloud Migration Experience (Y/N):
Cloud Cyber Security Expertise (Y/N):
Application Security Expertise (Y/N):
Operating System Familiarity:
Knowledge of Compliance Frameworks:
TEAM MEMBER
Name:
Cloud Experience (Years):
Cloud Areas of Expertise:
Cloud Migration Experience (Y/N):
Cloud Cyber Security Expertise (Y/N):
Application Security Expertise (Y/N):
Operating System Familiarity:
Knowledge of Compliance Frameworks:
TEAM MEMBER
Name:
Cloud Experience (Years):
Cloud Areas of Expertise:
Cloud Migration Experience (Y/N):
Cloud Cyber Security Expertise (Y/N):
Application Security Expertise (Y/N):
Operating System Familiarity:
Knowledge of Compliance Frameworks:
TEAM MEMBER
Name:
Cloud Experience (Years):
Cloud Areas of Expertise:
Cloud Migration Experience (Y/N):
Cloud Cyber Security Expertise (Y/N):
Application Security Expertise (Y/N):
Operating System Familiarity:
Knowledge of Compliance Frameworks:

## Application Assessment
APPLICATION ASSESSMENT
Use this sheet as an assessment of an application targeted for migration.
APPLICATION NAME | Omni-Pivot - Online transaction processing platform.
OWNER NAME | Owner Name
OWNER DEPARTMENT | Department Name
LOCATION | /DataCenter/PHX
PURPOSE | Use this sheet as an assessment of an application targeted for migration.
MIGRATION STRATEGY | REVISE
TARGET CLOUD ENVIRONMENT | Public Cloud, Hosted Private Cloud, On-Premise Private Cloud, Other
PRIORITY | Group 1
OPERATING SYSTEM(S) (Specific Versions)
COMMUNICATION PORT(S)
IMPORTANCE
What stage is this application (Production, Development, or Testing/QA/Staging)?
What is the nature or use case of the application?
Does the application have a clear direct or indirect impact to customers or external parties? (Y/N)
Does the application have a significant direct or indirect impact to business operations? (Y/N)
Overall Sensitivity to the business of any disruption (Very Low, Low, Medium, High, Mission Critical) | High
What is the application's Recovery Time Objective (RTO)?
What is the application's Recovery Point Objective (RPO)?
INTERDEPENDENCIES
Interdependency 1
Interdependency 2
Interdependency 3
Interdependency 4
Interdependency 5
ADDITIONAL APPLICATION REQUIREMENTS
Does the application require database resources? (Provide detail)
Does the application require data storage resources? (Provide detail)
What is the classification for associated data the application processes, transmits/transfers or stores?
Are there ancillary services this application relies on or feeds? (Provide detail)
LICENSING
Identify any vendor licensing that applies to this application:
Does current licensing cover usage in the targeted cloud environment? (Y/N)
Can licensing be expanded to cover usage in the targeted cloud environment? (Y/N)
Current licensing cost:
Additional licensing cost:
Cost of support infrastructure (network, bandwidth, servers, etc.)
SECURITY AND COMPLIANCE REQUIREMENTS
COMPLIANCE FRAMEWORKS
Identify compliance frameworks the application is subject to: | Ex. PCI DSS, HIPAA/HITRUST, GDPR
Identify specific controls the application must address:
- Ex. Access Control | PCI DSS 7.1.1, 7.1.2
- Ex. Intrusion Detection | PCI DSS 11.4
- Ex. File Integrity Monitoring | PCI DSS 11.5
- Ex. Other | XYZ 1.0
SECURITY FRAMEWORKS
Identify any security frameworks applied to the application: | Ex. NIST CSF, CIS Controls, etc.
- Ex. Access Control
- Ex. Intrusion Detection
- Ex. File Integrity Monitoring
- Ex. Other
IDENTITY AND ACCESS MANAGEMENT
Identify access privilege levels that exist with the application:
Identify individuals and/or parties that currently have access:
- Ex. Privilege Level (Admin)
- Ex. Privilege Level (Advanced User)
- Ex. Privilege Level (General User)
ENCRYPTION
Data at Rest (Y/N)
Data In Transit (Y/N)
What other encryption requirements does this app need to have?
WEB APPLICATION FIREWALL
Is this a web application (ex. Website, online platform, etc.?) (Y/N)
- If yes, do you need WAF functionality? (Y/N)
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Your "Migration Strategy" (based on Gartner 5Rs or other approach, should only be determined once all information has been collected on a given application with determination made by the overall migration team.

## Application Inventory
APPLICATION INVENTORY
PURPOSE: Use this sheet as a master list of applications assessed and prioritized for migration.
Application Name | Application Location | Apllication Function | Migration Strategy | Priority | Overall Sensitivity | Targeted Environment | Production or Development
Online Payment Application |  | Provides a invoicing/billing and payment platform for customers to purchase services. | Revise | Group 1 | High | Public Cloud - AWS | Production

## PLANNING FOR RETIREMENT
PLANNING FOR RETIREMENT
Purpose: Planning for the retirement of legacy environments, networks, applications and data repositories is almost as important as the migration itself. You need to be thinking about how your team will decommission assets and effect their disposal as quickly and as reasonably as possible. After all, as long as both environments remain up-and-running, your organization will fail to capture all of the returns on investment you should expect, and what you have planned for, for your cloud migration efforts.
Decommission Project Owner: | Name/Title
Corporate Investment Recovery (CIR) Team for Disposition of Assets | Team
Third Party Resource for Disposition of Assets | Name/Title
Eligible for: (Y/N)
Asset Type | Asset Name | Asset Tag | Owner(s) | Is the asset OWNED, LEASED or LICENSED? | Asset Virtual Location | Asset Physical Location | Running Application(s), If Applicable | Target Decommission Date | Reuse | Resale | Donate | Scrap | Has all hard drives been wiped and/or destroyed appropriate to policies? | Has asset been properly dispositioned (Reuse, Resale, Donate, Scrap)? | Has the asset been properly dispositioned in capital asset tracking system(s)? (Y/N or N/A) | If a license, has vendor been notified of transfer or termination of license?
Ex. Application Server
Ex. Storage (NAS)
Ex. Storage (SAN)
Ex. IDS Security Appliance
Ex. Web Application Firewall
Ex. Database Server
Ex. Software License
Ex. Cabling
Ex. Rack(s)
Ex. Backup Server or Array
Ex. Switch
Ex. DNS Server
Ex. Router
Ex, UPS

## Spreadsheet Elements
SPREADSHEET DROPDOWN ELEMENTS
THESE CAN BE MODIFIED AS YOU SEE FIT:
STATUS
Not Started
In Process
On Hold
Complete
Not Applicable
STAGE
Development
Testing/QA/Staging
Production
APPLICATION TYPE
Ecommerce application
Web 2.0/Social Networking
Internal enterprise application (e.g., HCM, Payroll, CRM, ERP)
Office productivity (e.g., Google Docs, Zoho)
Monitoring / Application Performance Management
Security/Compliance
Collaboration
Marketing/Business Intelligence
Other (please specify)